## Unified Audit
Record Identity | Record Identity | Drawing & Schedule | Drawing & Schedule | Drawing & Schedule | Drawing & Schedule | Cost & System | Cost & System | Cost & System | Cost & System | Item Identification | Item Identification | Item Identification | Item Identification | Field Quantities | Field Quantities | Field Quantities | Field Quantities | Earned Value | Earned Value | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Milestone Tracking | Work Packages & Planning | Work Packages & Planning | Work Packages & Planning | Work Packages & Planning | Work Packages & Planning | Work Packages & Planning | Work Packages & Planning | Performance Factors | Performance Factors | Performance Factors | Performance Factors | Performance Factors | Performance Factors | Performance Factors | Performance Factors | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Variance & Supplemental | Earned Value Metrics | Earned Value Metrics | Earned Value Metrics | Earned Value Metrics | Earned Value Metrics
DISCIPLINE | REC_NO | DWG | REV_NO | SCHED_ID | CAREA | CODE | SYSTEM | LINE_AREA | CIRCUIT | TAG_NO | SPOOL_FR | DESC_ | SZE | FLD_QTY | UOM | FLD_WHRS | SPEC | ERN_QTY | EARN_WHRS | M1_PCT | M1_DESC | M2_PCT | M2_DESC | M3_PCT | M3_DESC | M4_PCT | M4_DESC | M5_PCT | M5_DESC | M6_PCT | M6_DESC | M7_PCT | M7_DESC | M8_PCT | M8_DESC | TEST_PKG | CWP | IWP_PLAN_NO | SPL_CNT | IWP_FOREMAN | IWP_GEN_FOREMAN | WHRS_UNIT | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | VAR_AREA | VAR2 | PAINT_SPEC | INSU_SPEC | HEAT_TRACE_SPEC | SERVICE | TA_BANK | TA_BAY | TA_LEVEL | PSLIP | WORK_TYPE | PCT_EARNED | ROC
ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL | ALL
Pipe | 101 | 120-DR-590-SHT01 | 0 | SCH-PIPE-01 | EASTSIDE FIREWATER | 08331 | DR | UG |  |  | 120-DR-590-SHT01-1 | Underground firewater piping | 02 | 136 | LF | 584.8 | 01HDPE | 13.6 | 58.48 | 100 | Receive | 100 | Stage | 25 | Erect | 0 | Connect | 0 | Support | 0 | Punch | 0 | Test | 0 | Post | TP-DR-001 | CWP-DR-01 | IWP-DR-001 | 1 | A. Rivera | J. Chen | 4.3 | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | UG |  |  |  |  | FIREWATER | B01 | BAY-02 | GRADE | PS-001 | PIPE-STD | 10% | 1
Pipe | 102 | 120-DR-590-SHT02 | 0 | SCH-PIPE-01 | EASTSIDE FIREWATER | 08331 | DR | UG |  |  | 120-DR-590-SHT02-1 | Underground firewater piping | 04 | 217 | LF | 933.1 | 01HDPE | 15.19 | 65.317 | 100 | Receive | 100 | Stage | 10 | Erect | 0 | Connect | 0 | Support | 0 | Punch | 0 | Test | 0 | Post | TP-DR-001 | CWP-DR-01 | IWP-DR-002 | 1 | A. Rivera | J. Chen | 4.3 | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | UG |  |  |  |  | FIREWATER | B01 | BAY-02 | GRADE | PS-002 | PIPE-STD | 7% | 1
Pipe | 103 | 120-DR-591-SHT01 | 0 | SCH-PIPE-01 | EASTSIDE FIREWATER | 08331 | DR | UG |  |  | 120-DR-591-SHT01-1 | Underground firewater piping | 06 | 142 | LF | 610.6 | 01HDPE | 1.42 | 6.106 | 50 | Receive | 0 | Stage | 0 | Erect | 0 | Connect | 0 | Support | 0 | Punch | 0 | Test | 0 | Post | TP-DR-001 | CWP-DR-01 | IWP-DR-003 | 1 | A. Rivera | J. Chen | 4.3 | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | UG |  |  |  |  | FIREWATER | B01 | BAY-02 | GRADE | PS-003 | PIPE-STD | 1% | 1
Pipe | 104 | 120-DR-591-SHT02 | 0 | SCH-PIPE-01 | EASTSIDE FIREWATER | 08331 | DR | UG |  |  | 120-DR-591-SHT02-1 | Underground firewater piping | 08 | 98 | LF | 421.4 | 01HDPE | 0.49 | 2.107 | 25 | Receive | 0 | Stage | 0 | Erect | 0 | Connect | 0 | Support | 0 | Punch | 0 | Test | 0 | Post | TP-DR-001 | CWP-DR-01 | IWP-DR-004 | 1 | A. Rivera | J. Chen | 4.3 | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | UG |  |  |  |  | FIREWATER | B01 | BAY-02 | GRADE | PS-004 | PIPE-STD | 0.5% | 1
Pipe | 105 | 120-DR-592-SHT01 | 0 | SCH-PIPE-01 | EASTSIDE FIREWATER | 08331 | DR | UG |  |  | 120-DR-592-SHT01-1 | Underground firewater piping | 10 | 75 | LF | 295 | 01CS150 | 1.725 | 6.785 | 100 | Receive | 10 | Stage | 0 | Erect | 0 | Connect | 0 | Support | 0 | Punch | 0 | Test | 0 | Post | TP-DR-001 | CWP-DR-01 | IWP-DR-005 | 1 | A. Rivera | J. Chen | 3.9333 | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | UG |  |  |  |  | FIREWATER | B01 | BAY-02 | GRADE | PS-005 | PIPE-STD | 2.3% | 1